## Sheet1
Project Name |  | Project Duration |  | project start date |  | project end date
|  | 62 days |  | 4 Oct, 2019 |  | 10 Dec,2019
THE IMPACT OF E-GOVERNMENT IN PUBLIC SECTOR
Task ID | Task Description |  | Task Duration |  | Start | End Date
1 | Import Data |  | 2 |  | 2019-10-04 | 6 0ct,2019
2 | Data Cleaning |  | 8 |  | 2019-10-07 | 7 oct,2019
3 | Exploring Data variable |  | 5 |  | 2019-10-15 | 20 Oct,2019
4 | Exploring capital gain/loss |  | 8 |  | 2019-10-20 | 28 Oct,2019
5 | Exploring hour/weeks variable |  | 9 |  | 2019-10-29 | 7 Nov, 2019
6 | Exploring Work Class variable |  | 3 |  | 2019-11-08 | 10 Nov,2019
7 | Building Model |  | 9 |  | 2019-11-11 | 20 Nov, 2019
8 | Checking Accuracy |  | 5 |  | 2019-11-21 | 25 nov,2019
9 | Validate The Model |  | 10 |  | 2019-11-26 | 5 Dec ,2019
10 | Writing report |  | 3 |  | 2019-12-06 | 9 Dec,2019